## Experiment Setup Steps
The purpose of this tracker is to methodically go through each step and work with Split to complete. This covers the 'Split-specific' component parts and features to launch an A/B experiment.
Activity | Detail | Date | Completed
SPLIT IMPLEMENTATION
Events into Split | Send events, properties, values, impressions to Split |  | FALSE
Events validation | Validate the events are set up as expected with one of Splits Integration Advisors |  | FALSE
Define traffic types | The traffic type denotes the nature of the keys that are passed to getTreatment for that split. Does the key identify a known logged-in user? A device? Is the key a uuid generated for an anonymous visitor and stored in a cookie on the visitor’s browser? |  | FALSE
Define targeting | Use custom attributes or segments |  | FALSE
MEASUREMENT
Create a metric: primary | Create metrics for your experiment / per relevant traffic type |  | 0
Create a metric: secondary | Create metrics for your experiment / per relevant traffic type |  | 0
Create a metric: guardrail | Create metrics for your experiment / per relevant traffic type |  | 0
Create a metric: performance (engineering) | Create metrics for your experiment / per relevant traffic type |  | 0
Add metric tags | Create and assign metric tags to support analysis in Split |  | FALSE
Create a metric alert policy | Define and set metric alerts for key performance metrics |  | FALSE
DESIGN
Complete your experiment brief | Complete Split's experiemnt brief template or your own equaivalent version for your expeirment |  | 0
A/A TEST
Complete an A/A test | Run an A/A test to validate that your data is flowing and tracking as expected. Consider running on all new metrics, user journeys and features |  | 0
PLANNING
Set the ‘Experiment Settings’ for the relevant workspace (one off) | Define the appropriate experiment settings based on your requirements for this workspace (default statistical significance, minimum sample size, experiment review period and multiple comparison corrections) |  | 0
BUILD
Create a new Split | Create a split in the platform |  | 0
Define your treatments | Define and edit your treatments |  | 0
Attach configurations (if relevant) | Attach configurations to your treatments or editable components without a developer |  | 0
Set indiviual targets (if relevant) | Serve a treatment to particular customers and segments by individually targeting them |  | 0
Allocate traffic | Allocate the traffic percentage that is evaluated against the targeting rules and default rules |  | 0
Set targeting rules | Serve a treatment or percentage based on custom attributes, split dependencies or segments |  | 0
Set the default rule (% targeting) | Default rule: set a percentage to the remaining traffic |  | 0
Set the default treatment | Default treatment: set the default treatment for when the split is killed or the customer is not included in the traffic allocation |  | 0
Set the alert baseline treatments (if relevant) | Set the alert baseline treatment to be monitored against and measure the impact % for alert policies (created and defined at a metric-level) |  | 0
Click 'Review Changes' | Click the CTA to 'Review Changes' within the top right corner of the targeting rules page |  | 0
APPROVAL FLOW & PERMISSIONS
Set permission-levels | In the Split application, you can enable permissions by environment, split, segment, or metric, which limits the actions that non-editors can take. |  | 0
Define an approval flow | When reviewing or killing an experiment, define an approval flow in Split |  | 0
Click 'Save' | Hit 'save' to complete this step |  | 0
| ADD KEY METRICS |  | FALSE
Add 'Key' metrics | Navigate to the 'Metric Impact' tab and select up 5 metrics to add as a 'Key metric' e.g. these will be your primary and secondary metrics |  | 0
REVIEW / PEEKING
Select pre-analysis fields | Before reading the metrics impact dashboard, be sure to check the following: Split version, targeting, treatment and baselines, add any relevant filters and that the data is up to date |  | 0
Review the 'Summary' detail to check the current status | Check Split's application of pre-defined settings; statsitcal significance, experimental review period, sample ratio |  | 0
Review whether any alerts have been triggered | An alert banner will show in the 'targeting rules' tab and detail can be found in 'metrics impact' tab under the 'Alerts' section |  | 0
Review the metric impact cards | Check each metric impact card to determine the status of each metric and whether everything is as expected; e.g. not enough data, no comparison available, no associated events... |  | 0
ANALYSIS
Select pre-analysis fields | Before reading the metrics impact dashboard, be sure to check the following: Split version, targeting, treatment and baselines, and add any relevant filters |  | 0
Check the summary & metric cards | Is the experiment review period complete? is the sample valid? Has significance for key metrics been reached? Is the data up to date? |  | 0
Interpret the metric cards | Use the data within the metric cards to interpret the experiment results |  | 0
Interpret the metric impact graphs | Click into a metric card to interpret the graphs for a granular analysis for each metric |  | 0
SHARING
Share the results | Navigate to the 'share results' dropdown and choose a preferred format |  | 0

## Experiment Checklist
This checklist functions as a guide for the necessary/pitential steps to successfully deliver an end to end experiment.
Activity | Detail | Date | Completed
SPLIT IMPLEMENTATION
Events into Split | Send events, properties, values, impressions to Split |  | FALSE
Events validation | Validate the events are set up as expected with one of Splits Integration Advisors |  | FALSE
GOAL SETTING
Define company goals | E.g. increase revenue by 12% in 12 months |  | FALSE
Define business unit goals | E.g. retention, loyalty, online conversion |  | FALSE
Define optimization goals | E.g. AOV, CLTV, Conversion Rate |  | FALSE
Define experimentation goals | E.g. CTR, Engagement, Search, Bounce Rate, Conversions |  | FALSE
Define to goal for THIS experiment | E.g. increase Booking per User, which will impact Conversion, then impact RPV and ultimately Revenue to hit our 12% target |  | FALSE
IDEATION
What problem are you trying to solve? | What high friction experience have you encountered |  | FALSE
What qualitative data do you have to support this problem? | What customer feedback, user research or other data do you have |  | FALSE
What quantitative data do you have to support this problem? | What analytics, session recording or heatmap data do you have |  | FALSE
MEASUREMENT
What is your primary success metric? | Choose one measure for success. Ideally a sensitive metric to the change made |  | 0
What are your secondary success metrics? | Choose metrics in line with your down-funnel conversions e.g. revenue, completed bookings |  | FALSE
What are your behavioral guardrail metrics? | Choose metrics that are likely to be desirable/ undesirable based on improvement of your primary |  | FALSE
What are your performance (engineering) guardrail metrics? | Choose engineering metrics you want to monitor performance of |  | FALSE
HYPOTHESIS
Do you have a hypothesis statement? | A single statement defining your problem, solution, tactics and expected results |  | FALSE
DESIGN
Have you considered multiple solutions to your user problem? | Think creatively, what are 10 possible solutions to this problem. Testing multiple variations results in more audience insights |  | 0
Have you involved analytics, design and engineering teams? | Include as many relevant teams for a breath of ideas. Involving all teams also builds experimentation culture and buy in |  | 0
Have you considered the bigger picture? | Encourage and challenge teams to think iteratively. There is no ‘end’ to experimentation and innovation |  | 0
A/A TEST
Have you completed an A/A test? (if relevant) | Run an A/A test to validate that your data is flowing and tracking as expected. Consider running on all new metrics, user journeys and features |  | 0
PLANNING
Have you prioritized this experiment? | Leverage your own dedicated framework or Split’s shared resource to manage priority of build |  | 0
Have you considered priority amongst other team(s) experiments (if relevant) | If other teams are simultaneously experimenting, make sure there is no undesired overlap and check with all teams in a weekly sync |  | 0
Have you run a sample size calculation? | Run this for each experiment to determine minimum required sample, traffic and run times |  | 0
Have the ‘Experiment Settings’ for the relevant workspace been applied? (one off) | Check that the experiment settings are set up right for this workspace |  | 0
0
BUILD
Does your engineering team need to send any events to Split? | Confirm whether you are missing any events for metric creation and analysis in Split |  | 0
Does your engineering team have all experiment details? | Share your ‘experiment design brief’ with engineering so they know all details; events, metrics, treatment changes, targeting, rollout plans… |  | 0
Has the engineering team assigned Jira tickets for this experiment? | Such as A/A test completion, build, QA, launch, fixes, review period, phased roll out, flag management… |  | 0
QA & LAUNCH
Is there a QA plan for this experiment? | Is there a designated individual, team and process for completing QA |  | 0
Is there a launch or rollout plan for this experiment? (if relevant) | Is there dev time allocated in the event of a desired outcome, and therefore requires a roll out or permanent change |  | 0
REVIEW
Is there a review plan for once this experiment meets its duration and statistical threshold | Who is responsible for reviewing this, and when |  | 0
Are there clear next steps in place for all outcomes | E.g. Desired, undesired or inconclusive outcome; what actions will be taken |  | 0
ANALYSIS
What might you expect to find out after this experiment? | Think about this in the context of story telling e.g. what might users have done if not what you expected? |  | 0
Will there be any supporting qualitative data required? | For example, will you want to gather follow-up surveys or interviews? |  | 0
Will there be any supporting quantitative data required? | For example, will you want to gather follow-up heatmaps, session replays etc |  | 0
Will you need to secure analyst and/or data science resources for ROI, longtail, or further deep dive analysis? | For example, is the business expecting ROI reporting, or any down funnel behavioral analysis |  | 0
SHARING
Who is responsible for sharing results? | E.g. Product Owner, Product Manager, Analyst teams… |  | 0
Is there a framework or comms plan in place for this? | E.g. Who & how will it be shared? (WHO) C-Suite, organization-wide, tactical teams/ (HOW) email, product retro, stand ups, company all-hands, lunch & learns, roadshows, show & tells… |  | 0